## Sheet1
ODI website :: Main tasks appeared in website
*** | Frontpage functionality and addition function to existing backend
No | Task name | Description | Duration
1 | Update database follow the new functionality | Update existing DB follow to ODI requirement | 1 day
2 | Plus normal and active image to menu management | Update manage menu existing of backend with image | 1 day
3 | Add article with additional option display | Update Add article with option display with slideshow, training course or customize course | 1 day and half
4 | Manage Resources | Create new function for upload document into resource for member download | 2 days
5 | Manage Training course | Create new function for course list down, add, update and search | 2 days
6 | Manage Vacancy | Create new function for job list down, add, update and search | 2 days
7 | User Management | Create member for download resourse, account for manage training course or manage vacancy | 2 days
8 | List people who join training course | Create new function for list down people who join training course | 1 day
9 | Manage CV of candidate | Create new function for list down CV and download CV from candidate | 1 day
| Manage image follow to article | Create new function for image in article with position image top and text top | 1 day
10 | Design frontend interface | Cut image source into HTML , CSS and javacript template | 3 days and half
11 | Convert frontend into dynamic content | Convert HTML static page into dynamic follow Database resource | 5 days
12 | Create job alert function | Create subscript email for user who make condition match to the job vacancy that action or not expire.
| Share image or folder image to user | Create function for generate image or folder into linke for user download (generate file zip). | 2 days
13 | Upload CV and Training Course Register (frontend) | Create function upload user CV and register into training course | 1 day
|  | Total duration from each tasks | 26 days